## ABI vs DB Tracker
Sr No | Module | Abinitio | Databricks Pipeline Name | Resource Name | Priority | Completion Date | Percentage Compled | Status | Difference (Yes/No) | Comments
1 | CDD | 1000_CDD_PrePrep.pset | Pl_cdd_es_postbdf, pl_cdd_ie_postbdf, pl_leadrepo_escan_import_fc | Gopal | P1 | 2025-12-23 | 100% | Completed | NO | This is a pre-prep step for data preparation in CDD No actual business logic implemeted
2 | CDD | 1100_CDD_Charlotte271Data.pset | Pl_cdd_es_postbdf, pl_cdd_ie_postbdf, pl_leadrepo_escan_ich_import, pl_ich_xref, pl_leadservicebase | Ankur & Gopal | P1 | 2025-12-17 | 100% | In Review | No | Rework is needed as multiple pipelines are needed
3 | CDD | 1200_CDD_Charlotte271FamilyData.pset | Pl_leadrepository_xref_famc, pl_leadservicebase_famc | Gopal & Mohit Kumar | P1 | 2025-12-02 | 100% | In Review |  | In Review with Abdul
4 | CDD | 1300_CDD_PatientAcctsXRefPermID.pset | pl_cdd_bdf_download | Gopal & Mohit Naik | P1 | 2025-11-14 | 100% | Completed | YES | Below are the comments added by Finthrive- Large
5 | CDD | 1400_CDD_Charlotte271GMRNData.pset | Pl_cdd_es_postbdf, pl_cdd_ie_postbdf, pl_leadrepo_escan_ich_import, pl_ich_xref, pl_leadservicebase | Ankur & Gopal | P1 | 2025-12-19 | 100% | In Review | No
6 | CDD | 1500_CDD_TUSourcedFamilyMemberLink.pset | pl_TUSourcedFamilyMemberLink | Gopal & Mohit Naik | P1 | 2025-11-19 | 100% | Completed
7 | CDD | 1600_CDD_HFC_FamilyFoundCoverage.pset | Pl_leadrepository_xref_famc, pl_leadservicebase_famc | Gopal & Mohit Kumar | P1 | 2025-12-02 | 100% | In Review | No | In Review with Abdul
8 | CDD | 1700_CDD_HFC_RelatedMemberOPSourcedFC.pset | pl_leadrepo_escan_import_fc, pl_fc_xref, pl_leadservicebase | Gopal & Mohit Naik | P2 |  |  | In Review
9 | CDD | 2500_CDD_PropagateHFCForFamilyMembers.pset | Pl_leadrepository_xref_famc, pl_leadservicebase_famc | Gopal & Mohit Kumar | P1 | 2025-12-03 | 100% | In Review |  | In Review with Abdul
10 | CDD | 1800_CDD_HFC_Charlotte271Data.pset | pl_leadrepo_escan_import_fc, pl_fc_xref, pl_leadservicebase | Gopal & Mohit Naik | P1 | 2025-12-08 | 100% | In Review |  | In Review with Abdul
11 | CDD | 2000_CDD_LoadStagingAndCallSP.PatientAcctsXRefPermID.pset | Load to HelperFoundCoverage similar to loading LSB in pl_leadservicebase | Gopal & Mohit Kumar | P3 | 2025-12-16 |  | In Progress |  | Queued for DBX comparison
12 | CDD | 2000_CDD_LoadStagingAndCallSP.TUSourcedFamilyMemberLink.pset |  | Gopal & Mohit Kumar | P3 | 2025-12-16 |  | In Progress |  | Queued for DBX comparison
13 | CDD | 2000_CDD_LoadStagingAndCallSP.PatientAcctsXRefPermIDUpdate.pset |  | Gopal & Mohit Kumar | P3 | 2025-12-16 |  | In Progress |  | Queued for DBX comparison
14 | CDD | 2200_CDD_LoadHelperFoundCoveragesAndCallSP.pset |  | Gopal & Mohit Kumar | P3 | 2025-12-16 |  | In Progress |  | Queued for DBX comparison
15 | CDD | 2800_CDD_LoadHelperFoundCoveragesAndCallSP_Propagation.pset |  | Gopal & Mohit Kumar | P3 | 2025-12-16 |  | In Progress |  | Queued for DBX comparison
16 | Commerical Generation | 100_commGenPrePrep.pset | pl_leaddiscovery_globalmrn_assign, pl_leaddiscovery_lead_propagation, pl_leaddiscovery_leadverify, pl_leaddiscovery_known_commercial, pl_leaddiscovery_leadlookup_knowncommercial | Anjani & Mohit Kumar | P1 | 2025-12-24 | 100% | In Review
17 | Commerical Generation | 105_commGenPrePrep.pset |  | Anjani & Mohit Kumar | P1 | 2025-12-24 | 100% | In Review
18 | Commerical Generation | 102_commGenPrePrep.pset |  | Anjani & Mohit Kumar | P1 | 2026-01-16 | 80% | In Progress |  | Comparison is Pending
19 | Commerical Generation | 400_commGenIpa.pset |  | Anjani & Mohit Naik | P1 | 2025-12-24 | 100% | In Review
20 | Commerical Generation | 405_commGenPatcho.pset |  | Anjani & Mohit Naik | P1 | 2025-12-24 | 100% | In Review
21 | Commerical Generation | 410_commGenPrePA.pset |  | Anjani & Mohit Naik | P1 | 2025-12-24 | 100% | In Review
22 | Commerical Generation | 415_commGenResultGmrn.pset |  | Anjani & Mohit Naik | P1 | 2025-12-25 | 100% | In Review
23 | Commerical Generation | 420_commGenFinal.pset |  | Anjani & Mohit Naik | P1 | 2025-12-25 | 100% | In Review
24 | Commerical Generation | 430_commGenFinalCluster.pset |  | Anjani & Mohit Naik | P1 | 2025-12-25 | 100% | In Review
25 | Commerical Generation | 435_commGenClusteringReport.pset |  | Anjani & Mohit Naik | P1 | 2025-12-26 | 100% | In Review
26 | Commerical Generation | 500_comGenLoadFinalFile.pset |  | Anjani & Mohit Naik | P1 | 2025-12-26 | 100% | In Review
27 | Medicare Lead Generation | 505_GenLoadFinalFile.mCare.pset | pl_mbihelper pl_leaddiscovery_medicareleads pl_mh_import pl_leadservicebase_mh | Anjani & Mohit Naik | P1 | 2025-12-26 | 100% | Completed |  | 24/Dec - Comparison not required with Databricks
28 | Medicare Lead Generation | 120_mcarePrePrep.pset |  | Anjani & Mohit Kumar | P1 | 2025-12-08 | 100% | Completed |  | -mbihelper is completed -leaddiscovery_medicareleads completed
29 | Medicare Lead Generation | 440_mCareGenIpa.pset |  | Anjani & Mohit Kumar | P1 | 2025-12-04 | 100% | Completed |  | Abdul has reviewed the comparison
30 | Medicare Lead Generation | 445_mCareGenDsh.pset | [7 empty] | Out of Scope
31 | Medicare Lead Generation | 450_mCareGenHets.pset |  | Anjani & Mohit Kumar | P1 | 2025-12-04 | 100% | Completed
32 | Medicare Lead Generation | 455_mCareGenHetsOnly.pset |  | Anjani & Mohit Kumar | P1 | 2025-12-08 | 100% | Completed
33 | Medicare Lead Generation | 460_mCareGenFinal.pset |  | Anjani & Mohit Kumar | P1 | 2025-12-08 | 100% | Completed
34 | Data Ingestion | 200_extractDataFromSqlToAbi.pset | pl_dataingestion_fnf, pl_dataingestion_big_tables, pl_dataingestion_abi_group1, pl_dataingestion_abi_group2 | Gopal & Mohit Naik | P3 | 2026-01-15 |  | In Progress
35 | Data Ingestion | 300_extractDataFromSqlToAbi_FasterETL.pset |  | Gopal & Mohit Naik | P3 | 2026-01-15 |  | In Progress
36 | GHIC | 439_LoadvSnapGlobalMRNxHospInsuranceCodes.pset |  | Gopal & Mohit Naik | P3 | 2026-01-08 |  | In Review |  | No Comparison required.
37 | Data Ingestion | 600_consolidateArchiveCleanUp.pset |  | Gopal & Mohit Naik | P3 | 2026-01-13 |  | In Progress |  | Not required,No business/tranformation rules. Disk Housekeeping job to Archive older data file on disk
38 | Data Ingestion | 210_compareDataInAbiToSql.pset |  | Gopal & Mohit Naik | P3 | 2026-01-14 |  | In Progress
39 | Data Ingestion | 265_fileTransferToHadoopServer.pset |  | Gopal & Mohit Naik | P3 | 2026-01-14 |  | In Progress |  | Not required , No business/tranformation rules. File transfer job to Hadoop server

## HDP Vs DB Tracker
Sr No | Module | Hadoop Pipeline_Name | Databricks Pipeline Name | Resource Name | Priortiy | Completion Date | Percentage Compled | Status | Difference (Yes/No) | Comments | Hadoop Workflow Summary
1 | CDD | cdd: bcs_permid_swift | pl_cdd_es_prebdf | Ankur & Mohit Naik | P1 | 2025-11-13 | 100% | Completed | No | No differences found | Packages and sends PermID-related output via SWIFT for downstream/partner consumption.
2 | CDD | cdd: bdf_download | pl_cdd_bdf_download, pl_cdd_bdf_download_checkfile, pl_chc_bdf_download | Ankur & Mohit Naik | P1 | 2025-11-10 | 100% | Completed | Yes | Three differences were identified. FinThrive confirmed these as enhancements with no data impact, implemented to prevent duplicate file processing. | Downloads TransUnion BDF files used as input for coverage discovery post-processing.
3 | CDD | cdd: es-swift-postbdf | pl_cdd_es_postbdf | Ankur & Mohit Naik | P1 | 2025-11-13 | 100% | Completed | No | No differences found | Runs ES (eScan) post-BDF coverage discovery processing and publishes the processed results.
4 | CDD | IE-PREBDF | pl_cdd_ie_prebdf | Ankur & Mohit Naik | P1 | 2025-11-28 | 100% | Completed | Yes | One difference was found where Finthrive commented that it was a new change to limit the influx of less valuable leads from ICH | Runs IE (ICH) pre-BDF preparation to stage raw ICH messages for downstream CDD processing.
5 | CDD | cdd: ie-postbdf | pl_cdd_ie_postbdf | Ankur & Mohit Naik | P1 | 2025-12-04 | 100% | Completed | Yes | Two differences were identified. Finthrive commented as inactive in databricks as it is not necessary | Runs IE (ICH) post-BDF coverage discovery processing and writes coverage discovery outputs.
6 | CDD | TU-PREBDF | pl_tu_prebdf | Mohit Naik & Ankur | P3 | 2026-01-12 | 100% | In Review |  | As of now hold from Databricks perspective | Prepares/stages TransUnion-related inputs needed before BDF-driven processing steps run.
7 | CDD | cdd: family_clustering | pl_leadrepository_xref_famc | Mohit Naik & Ankur | P2 | 2025-01-05 | 100% | Completed |  |  | Groups related records into “family” clusters to support downstream matching/lead logic.
8 | Data Ingestion | escan_coverage_helper : > build repo | pl_mbihelper | Ankur & Mohit Naik | P3 | 2026-01-12 | 100% | In Review |  |  | Builds/refreshes the coverage helper repository/artifacts used by ingestion/processing jobs.
9 | Data Ingestion | escan_coverage_helpers : medicare_helper_selectaccts |  | Ankur & Mohit Naik | P3 | 2026-01-12 | 100% | In Review |  |  | Selects the Medicare-relevant account subset used for Medicare coverage helper processing.
10 | Data Ingestion | escan_data_ingestion : sqoop_fnf | pl_dataingestion_fnf | Ankur & Mohit Naik | P3 | 2026-01-12 | 100% | In Review |  |  | Sqoop-ingests “fnf” source tables from SQL Server into the raw (bronze) landing area.
11 | Data Ingestion | escan_data_ingestion : lsb_conf_tables_fnf |  | Ankur & Mohit Naik | P3 | 2026-01-12 | 100% | In Review |  |  | Ingests/configures LSB configuration tables (fnf set) required for Lead Service Base processing.
12 | Data Ingestion | escan_data_ingestion : big_tables | pl_dataingestion_big_tables | Ankur & Mohit Naik | P3 | 2026-01-13 | 100% | In Review |  |  | Ingests large/high-volume tables with a configuration optimized for “big table” loads.
13 | Data Ingestion | escan_data_ingestion : sqoop_table |  | Ankur & Mohit Naik | P3 | 2026-01-13 | 100% | In Review |  |  | Sqoop-ingests a specified single table from SQL Server into Hadoop.
14 | Data Ingestion | escan_data_ingestion : ingest_all | pl_dataingestion_abi_group1, pl_dataingestion_abi_group2 | Ankur & Mohit Naik | P3 | 2026-01-13 | 100% | In Review | No |  | Runs the standard “ingest everything” load to refresh raw eScan datasets in Hadoop.
15 | Data Ingestion | escan_data_ingestion:SA-WF:foundcoverage |  | Ankur & Mohit Naik | P3 | 2026-01-13 | 100% | In Review | No |  | Ingests/stages “found coverage” inputs used by lead repository and downstream lead generation.
16 | Data Ingestion | escan_data_ingestion:SA-WF:patientaccts |  | Ankur & Mohit Naik | P3 | 2026-01-13 | 100% | In Review | No |  | Ingests/stages patientaccts (patient account data) into the raw landing zone.
17 | Data Ingestion | escan_data_ingestion : sdob_ingestion |  | Ankur & Mohit Naik | P3 | 2026-01-13 | 100% | In Review | No |  | Ingests/stages SDOB-related datasets used for DOB enrichment/matching workflows.
18 | Data Ingestion | escan_data_ingestion : swift_ingest_all |  | Ankur & Mohit Naik | P3 | 2026-01-13 | 100% | In Review | No |  | Executes a full ingestion run where inputs/outputs are exchanged via SWIFT-based file movement.
19 | Data Ingestion | escan_data_ingestion : >ingest_table - |  | Ankur & Mohit Naik | P3 | 2026-01-13 | 100% | In Review | No |  | Ad-hoc ingestion of a specific table into Hadoop (single-table ingest entry point).
20 | Data Ingestion | escan_data_ingestion : >ingest_table_DLAKE - |  | Ankur & Mohit Naik | P3 | 2026-01-13 | 100% | In Review | No |  | Ingests a specified table directly into Delta Lake–managed storage for downstream serving/updates.
21 | Data Ingestion | escan_data_ingestion : chc | pl_chc_import | Ankur & Mohit Naik | P2 | 2025-01-05 | 100% | Completed |  |  | Ingests CHC carrier files (download/parse) and lands the results for downstream processing.
22 | Data Ingestion | escan_data_ingestion : CHC_ID |  | Ankur & Mohit Naik | P2 | 2025-01-06 | 100% | Completed |  |  | Ingests/derives CHC identifier mappings used to link CHC records to internal entities.
23 | Data Ingestion | escan_data_ingestion : CHC |  | Ankur & Mohit Naik | P2 | 2025-01-06 | 100% | Completed |  |  | Loads CHC carrier data into Hadoop in the standardized raw/landing structure.
24 | Data Ingestion | escan_data_ingestion : CHC_PERM_GMRN_ID_XREF | pl_chc_xref | Ankur & Mohit Naik | P2 | 2025-01-06 | 100% | Completed |  |  | Builds/ingests crosswalks between PermID, GMRN, and CHC identifiers for identity linkage.
25 | GMRN | escan_globalmrn : ghic | pl_gmrn_ghic | Ankur & Mohit Naik | P3 | 2026-01-14 | 100% | In Review |  |  | Runs GHIC-related matching/assignment logic as part of global MRN identity resolution.
26 | GMRN | escan_globalmrn : merge | pl_gmrn_merge pl_gmrn_merge_sub | Ankur & Mohit Naik | P1 | 2025-12-26 | 100% | Completed | Yes | Two Differences were identified and implemeted to support sharding | Merges patient accounts and global MRN demographics to produce consolidated/merged GMRN data.
27 | Lead Discovery | leaddiscovery: leadlookup: | pl_leaddiscovery_globalmrn_assign (CommerciaL) | Ankur & Mohit Naik | P1 | 2025-12-18 | 100% | Completed | Yes | Two differences were identified wherein Finthrive commented as enhancements in order to manage the quality and volume of leads | Looks up candidate leads from serving/xref datasets to seed downstream lead discovery flows.
28 | Lead Discovery | leaddiscovery: medicareleads | pl_leaddiscovery_medicareleads | Ankur & Mohit Naik | P1 | 2025-12-11 | 100% | Completed | Yes | Additional filter in databricks. This is an enhancements | Generates Medicare-focused leads using rules/data specific to Medicare discovery.
29 | Lead Discovery | leaddiscovery: medicaidleads | pl_leaddiscovery_medicaidleads | Ankur & Mohit Naik | P1 | 2025-12-11 | 100% | Completed | Yes | Databricks has additional time-based filtering in patient account selection stage, when lead_mode = 1 with configurable days (default 365 days). Hadoop uses hardcoded 3 days. ( Enhancement logic) | Generates Medicaid-focused leads using rules/data specific to Medicaid discovery.
30 | Lead Discovery | leaddiscovery: lead propagation | pl_leaddiscovery_lead_propagation | Ankur & Mohit Naik | P2 | 2025-01-07 | 100% | Completed |  |  | Propagates/enriches leads across related entities using xrefs and linkage rules.
31 | Lead Discovery | leaddiscovery: leadverify | pl_leaddiscovery_leadverify | Ankur & Mohit Naik | P2 | 2025-01-07 | 100% | Completed |  |  | Validates/verifies generated leads (quality checks, eligibility, de-duplication).
32 | Lead Discovery | subdob :data mining | pl_leaddiscovery_subdob | Ankur & Mohit Naik | P2 | 2025-01-08 | 100% | Completed |  |  | Mines data to infer/enrich DOB (or DOB-related signals) to improve matching/lead quality.
33 | Lead Discovery | leaddiscovery:known_commercial | pl_leaddiscovery_known_commercial | Ankur & Mohit Naik | P2 | 2025-01-08 | 100% | In Review |  |  | Generates leads for known commercial populations using commercial-specific criteria.
34 | Lead Discovery | lead discovery: leadlookup: knowncommercial | pl_leaddiscovery_leadlookup_knowncommercial | Ankur & Mohit Naik | P2 | 2025-01-09 | 100% | In Review |  |  | Performs lead lookup specifically scoped to the known-commercial segment.
35 | Lead Repository | leadrepository : escan_import_fc | pl_leadrepo_escan_import_fc | Ankur & Mohit Naik | P1 | 2025-12-18 | 100% | Completed | Yes | Three differences were identified. Finthrive confirmed as enhancements to remove bad leads from FC | Imports “found coverage” into the lead repository store for consolidation and downstream use.
36 | Lead Repository | leadrepository : famc_xref_table_update | pl_leadrepository_xref_famc | Ankur & Mohit Naik | P2 | 2025-01-09 | 100% | In Review |  |  | Updates family/cluster cross-reference tables used to relate entities during lead processing.
37 | Lead Repository | leadrepository : ich_import_parse | pl_leadrepo_escan_ich_import | Ankur & Mohit Naik | P1 | 2025-12-25 | 100% | Completed | Yes | Additional filter codes are added for better quality leads | Imports and parses ICH coverage history/messages into lead repository-ready structures.
38 | Lead Repository | lead repository: xref | pl_leadrepository_xref, pl_ich_xref, pl_fc_xref, pl_globalmrn_xref | Ankur & Mohit Naik | P1 | 2025-12-23 | 100% | Completed | Yes | Four differences were identified and validated by FinThrive as enhancements designed to control volume and improve the identification of high-value leads from FC. | Builds/updates cross-reference (xref) tables that link identities (e.g., PermID/GMRN) to leads.
39 | Lead Service Base | leadservicebase : lead gen and update : chc | pl_leadservicebase_chc | Ankur & Mohit Naik | P3 | 2026-01-14 | 100% | In Review |  |  | Generates/updates Lead Service Base records specifically from CHC-derived inputs.
40 | Lead Service Base | leadservicebase : lead gen and update | pl_leadservicebase pl_leadservicebase_gmrnmerge | Ankur & Mohit Naik | P1 | 2025-12-26 | 100% | Completed | No | No differences found | Populates and updates the Lead Service Base serving layer from consolidated lead repository inputs.
41 | Ops Hint | process-hints | pl_hintsdiscovery_commercial | Ankur & Mohit Naik | P3 | 2026-01-15 | 100% | In Review |  |  | Processes operational “hints” metadata used to guide, prioritize, or debug workflow execution.
42 | Lead Service Base | leadstatus: upsert | [7 empty] | No pipeline to compare | Upserts lead status records (insert/update) so downstream consumers see current lead state.
43 |  |  | pl_dataingestion_abi_group1_aid
44 |  |  | pl_leaddiscovery_globalmrn_assign_aid
45 |  |  | pl_leaddiscovery_medicaidleads_aid
46 |  |  | pl_leaddiscovery_medicareleads_aid
47 |  |  | pl_leaddiscovery_birthmonth
48 |  |  | pl_TUSourcedFamilyMemberLink
49 |  |  | pl_hintsdiscovery_payer_ops_widescan
50 |  |  | pl_leadservicebase_famc
51 |  |  | pl_leadservicebase_mh
52 |  |  | pl_medicaidhelper
53 |  |  | pl_mh_import
54 |  |  | pl_blacklisted_accounts
55 |  |  | pl_gmrn_family_helper

## Consolidated
P1 - Comparison | Module | Priority - 1
|  | Total P1 | In-progress | Comparing | Review | Completed | % Completion
Abinitio vs Databricks | CDD | 9 | 0 | 0 | 6 | 3 | 33.33%
| Medicare | 6 | 0 | 0 | 0 | 6 | 100%
| Commercial | 10 | 0 | 0 | 10 | 0 | 0%
| GHIC | - | - |  |  | - | -
| Data Ingestion | - | - |  |  | - | -
|  | 25 | 0 | 0 | 16 | 9
P2 - Comparison | Module | Priority - 2
|  | Total P2 | In-progress | Comparing | Review | Completed | % Completion
Abinitio vs Databricks | CDD | 1 |  |  | 1 | 0
| Medicare | - | - |  |  | - | -
| Commercial | - | - |  |  | - | -
| GHIC | - | - |  |  | - | -
| Data Ingestion | - | - |  |  | - | -
|  | 1 | 0 | 0 | 1 | 0 | 0
P3 - Comparison | Module | Priority - 3
|  | Total P3 | In-progress | Comparing | Review | Completed | % Completion
Abinitio vs Databricks | CDD | 5 | 5 |  |  | 0 | 0
| Medicare | - | - |  |  | - | -
| Commercial | - | - |  |  | - | -
| GHIC | 1 |  |  | 1 | 0 | 0
| Data Ingestion | 5 | 5 |  |  | 0 | 0
|  | 11 | 10 | 0 | 1 | 0 | 0
P1 - Comparison | Module | Priority - 1
|  | Total P1 | In-progress | Comparing | Review | Completed | % Completion
Hadoop vs Databricks | CDD | 5 | 0 | 0 | 0 | 5 | 100%
| Lead Discovery | 3 | 0 | 0 | 0 | 3 | 100%
| Lead Repository | 3 | 0 | 0 | 0 | 3 | 100%
| Lead Service Base | 1 | 0 | 0 | 0 | 1 | 100%
| GMRN | 1 | 0 | 0 | 0 | 1 | 100%
| Data Ingestion | - | - | - | - | - | -
| OPS Hint | - | - | - | - | - | -
|  | 13 | 0 | 0 | 0 | 13 | 100%
P2 - Comparison | Module | Priority - 2
|  | Total P2 | In-progress | Comparing | Review | Completed | % Completion
Hadoop vs Databricks | CDD | 1 | 0 | 0 | 0 | 1 | 100%
| Lead Discovery | 5 | 0 | 0 | 0 | 5 | 100%
| Lead Repository | 1 | 0 | 0 | 0 | 1 | 100%
| Lead Service Base | - | - | - | - | - | -
| GMRN | - | - | - | - | - | -
| Data Ingestion | 4 | 0 | 0 | 0 | 4 | 100%
| OPS Hint | - | - | - | - | - | -
|  | 11 | 0 | 0 | 0 | 11 | 100%
P3 - Comparison | Module | Priority - 3
|  | Total P3 | In-progress | Comparing | Review | Completed | % Completion
Hadoop vs Databricks | CDD | 1 | 0 | 0 | 1 | 0
| Lead Discovery | - | - | - | - | - | -
| Lead Repository | - | - | - | - | - | -
| Lead Service Base | 1 | 0 | 1 |  | 0 | 0
| GMRN | 1 | 0 | 1 |  | 0 | 0
| Data Ingestion | 13 | 2 | 13 |  | 0 | 0
| OPS Hint | 1 | 0 | 1 |  | 0 | 0
|  | 17 | 2 | 16 | 1 | 0 | 0
P1 | Total P1 | In-progress | Comparing | BBi Completed | BBI Completion % (Review Pending) | FinThrive Review | FinThrive SignOff Completed | Overall Completion % (Finthrive Signoff)
ABI vs DB | 25 | 0 | 0 | 25 | 100% | 16 | 9 | 36%
HD vs DB | 13 | 0 | 0 | 13 | 100% | 0 | 13 | 100%
Total P1 | 38 | 0 | 0 | 38 | 100% | 16 | 22 | 57.89%
P2 | Total P2 | In-progress | Comparing | BBi Completed | BBI Completion % (Review Pending) | FinThrive Review | FinThrive SignOff Completed | Overall Completion % (Finthrive Signoff)
ABI vs DB | 1 | 0 | 0 | 1 | 100% | 1 | 0 | 0%
HD vs DB | 11 | 0 | 0 | 11 | 100% | 6 | 5 | 45.45%
Total P2 | 12 | 0 | 0 | 12 | 100% | 7 | 5 | 41.67%
P3 | Total P3 | In-progress | Comparing | BBi Completed | BBI Completion % (Review Pending) | FinThrive Review | FinThrive SignOff Completed | Overall Completion % (Finthrive Signoff)
ABI vs DB | 12 | 10 | 0 | 1 | 8.333% | 1 | 0 | 0%
HD vs DB | 18 | 0 | 18 | 0 | 0% | 0 | 0 | 0%
Total P1 | 30 | 10 | 18 | 1 | 3.333% | 1 | 0 | 0%
Overall | Total P1+P2+P3 | In-progress | Comparing | BBi Completed | BBI Completion % (Review Pending) | FinThrive Review | FinThrive SignOff Completed | Overall Completion % (Finthrive Signoff)
ABI vs DB | 38 | 10 | 0 | 27 | 71.05% | 18 | 9 | 23.68%
HD vs DB | 42 | 0 | 18 | 24 | 57.14% | 6 | 18 | 42.86%
Total overall | 80 | 10 | 18 | 51 | 63.75% | 24 | 27 | 33.75%